## 0. Guidance & Instructions
MANUAL TESTING DOCUMENTATION GUIDE
1. TEST PLAN
Purpose: Defines overall testing approach, scope, timeline, and resources.
Key Components: Project info, scope, testing types, environment, timeline, resources, risks, assumptions.
Who fills it: QA Lead/Test Manager
When: Before testing begins
2. TEST SCENARIOS
Purpose: Describes high-level business situations/workflows to be tested.
Key Components: Scenario ID, name, description, pre-conditions.
Who fills it: QA Lead/Business Analyst
When: During test planning phase
Example: "User Login Scenario" - User provides credentials and system validates them
3. TEST CASES
Purpose: Detailed step-by-step instructions for testing specific functionality.
Key Components: Test case ID, scenario ID, title, pre-conditions, steps, expected result, priority.
Who fills it: QA Engineer/SDET
When: During test design phase
Best Practice: Each test case should be independent and reusable
4. TEST DATA
Purpose: Documents all test data needed for test execution.
Key Components: Data ID, type, test data values, purpose/usage.
Who fills it: QA Engineer/Test Data Manager
When: Before test execution
Important: Use realistic but safe data; never use real production data
5. TEST EXECUTION DOCUMENT
Purpose: Records actual execution results of test cases.
Key Components: Test case ID, cycle, title, executed by, execution date, pass/fail status, defect ID.
Who fills it: QA Engineer
When: During test execution
Status Options: Pass (expected behavior matches actual), Fail (discrepancy found), Not Executed (skipped)
6. TRACEABILITY MATRIX
Purpose: Maps requirements to test cases to ensure complete coverage.
Key Components: Requirement ID, test case ID, requirement description, coverage status.
Who fills it: QA Lead
When: Throughout testing lifecycle
Benefit: Identifies gaps; ensures all requirements are tested
7. DEFECT REPORT
Purpose: Documents all defects/bugs found during testing.
Key Components: Defect ID, test case ID, title, description, severity, priority, status, assigned to.
Who fills it: QA Engineer
When: When defect is discovered
Severity: Critical (blocks functionality), High (major issue), Medium (moderate impact), Low (minor issue)
Priority: Should be set based on business impact
8. TEST SUMMARY REPORT
Purpose: High-level overview of testing results and recommendations.
Key Components: Execution summary, defect summary, metrics, conclusion, recommendation.
Who fills it: QA Lead/Test Manager
When: At end of test cycle
Audience: Stakeholders, Project Manager, Development Lead
KEY METRICS
Pass Rate = (Test Cases Passed / Test Cases Executed) × 100%
Requirement Coverage = (Requirements Tested / Total Requirements) × 100%
Defect Density = Total Defects / Total Test Cases
Escape Rate = Defects found in production / Total defects found (in testing + production)

## 1. Test Plan
TEST PLAN
Project Name: | Notes App — UI + API Automation
Test Plan ID: | TP-001
Version: | 1.0
Date: | 06-05-2026
Prepared By: | Saniya Thabassum
Approved By: | QA Lead
SCOPE
Features to be Tested: | 1. UI Login (valid and invalid)
2. Create Note via UI
3. Note visible in UI instantly after creation
4. API GET /notes - list and response time
5. UI-created note matches API response
6. Delete note via API
7. API-deleted note disappears from UI
8. Negative UI and API scenarios
Out of Scope | 1. Performance load testing
2. Mobile browser testing
3. Third-party integrations
TESTING TYPE
Functional Testing | ☐
Regression Testing | ☐
Integration Testing | ☐
UAT | ☐
TEST ENVIRONMENT | Dev / QA / Staging / Production
Application URL(UI) | https://practice.expandtesting.com/notes/app
Application URL(API) | https://practice.expandtesting.com/notes/api
Browser | Chrome (latest version)
Operating System | Windows 11
Test Framework | Selenium + Python + Pytest + Requests
TIMELINE | 2026-05-06
Start Date: | 2026-05-08
End Date:
RESOURCES
QA Lead: | Static credentials in config.yaml + dynamic API data
QA Resources:
Test Data Provider:
RISKS & ASSUMPTIONS
Risks
Risk 1: | Locators may change with application updates
Risk 2: | API token may expire during long test runs
Risk 3: | Network latency may affect response time assertions
Assumptions:
Assumption 1 | Test account is pre-created on ExpandTesting
Assumption 2 | Application is accessible during test execution
Assumption 3 | Python 3.10+ and Chrome browser are installed

## 2. Test Scenarios
Scenario ID | Scenario Name | Description | Pre-conditions
SC-001 | UI Login - Valid Credentials | Validate that a registered user can log in successfully using valid email and password via the Notes App UI. | User account exists on ExpandTesting App is accessible
SC-002 | Create Note via UI | Validate that a logged-in user can create a new note by entering Category, Title and Description and clicking Save. | User is logged in Notes list page is open
SC-003 | Note Appears Instantly in UI Without Refresh | Validate that after saving a note, it appears in the notes list immediately without requiring a page reload. | User is logged in Note creation form is submitted
SC-004 | API GET /notes Returns List | Validate that the GET /notes endpoint returns status 200, a list of notes, and responds within 2 seconds. | Valid API auth token obtained via POST /users/login
SC-005 | UI-Created Note Matches API Response | Validate end-to-end consistency: a note created in the UI must appear in the API GET /notes response with matching title and description. | User logged in on UI API client authenticated
SC-006 | Delete Note via API | Validate that sending DELETE /notes/{id} removes the note and subsequent GET /notes no longer returns it. | Note exists in system API client authenticated with valid token
SC-007 | API-Deleted Note Disappears from UI | Validate that after deleting a note via API, refreshing the UI notes list shows the note is gone with no ghost entries. | Note exists in both UI and API API client authenticated
SC-008 | Negative UI Scenarios | Validate that the UI correctly handles invalid inputs: wrong credentials show an error message and empty fields are rejected. | Notes App login page is accessible
SC-009 | Negative API Scenarios | Validate that the API returns correct HTTP error codes: 401 for missing token, 404 for non-existent note, 400 for missing fields. | API endpoint is accessible

## 3. Test Cases
Test Case ID | Scenario ID | Test Case Title | Pre-conditions | Steps | Expected Result | Priority | Status
TC-001 | SC-001 | Valid UI Login | Login page is open Valid account exists on ExpandTesting | 1. Open the login page 2. Enter valid email address 3. Enter valid password 4. Click the Login button | User is redirected to the Notes list page URL contains /app | High | Not Started
TC-002 | SC-001 | Invalid UI Login - Wrong Password | Login page is open | 1. Open the login page 2. Enter valid email address 3. Enter wrong password 4. Click the Login button | Error message is displayed on screen User remains on the login page | High | Not Started
TC-003 | SC-001 | Invalid UI Login - Empty Fields | Login page is open | 1. Open the login page 2. Leave email field blank 3. Leave password field blank 4. Click the Login button | Validation error is shown Form is not submitted | Medium | Not Started
TC-004 | SC-002 | Create Note via UI - All Fields | User is logged in Add Note button is visible | 1. Click the Add Note button 2. Select Category as Home 3. Enter Title: My Test Note 4. Enter Description: Test description text 5. Click the Save button | Success message is displayed Note appears in the notes list | High | Not Started
TC-005 | SC-003 | Note Visible Immediately After Creation | User is logged in Note has just been created via TC-004 | 1. Complete note creation steps from TC-004 2. Do NOT refresh the page 3. Observe the notes list on screen | Newly created note title is visible in the list No page reload was needed | High | Not Started
TC-006 | SC-004 | API GET /notes - Status and Schema | Valid auth token has been obtained | 1. Send POST /users/login with valid credentials to get token 2. Send GET /notes with header x-auth-token set to the token | Status code is 200 Response body contains key called data data is a list Each item has id, title, description and category | High | Not Started
TC-007 | SC-004 | API GET /notes - Response Time Less Than 2 Seconds | Valid auth token has been obtained | 1. Send POST /users/login 2. Send GET /notes 3. Record the elapsed response time | Response time is less than 2.0 seconds | High | Not Started
TC-008 | SC-005 | UI-Created Note Matches API - Title and Description | User is logged in on UI API client is authenticated | 1. Create note via UI with Title: E2E Note and Description: Sync check 2. Send GET /notes via API 3. Find the note in API response where title equals E2E Note 4. Compare the description field | API response contains the note Title matches exactly Description matches exactly | High | Not Started
TC-009 | SC-006 | Delete Note via API - Confirmed Removal | Note exists in the system API client is authenticated | 1. Send POST /notes via API to create a note and capture the id 2. Send DELETE /notes/{id} via API 3. Send GET /notes via API again | DELETE request returns status 200 Subsequent GET /notes does not contain the deleted note id | High | Not Started
TC-010 | SC-007 | API-Deleted Note Gone from UI | API client is authenticated UI login credentials are available | 1. Create a note via API and capture the id 2. Send DELETE /notes/{id} via API 3. Open browser and login via UI 4. Navigate to notes list page 5. Refresh the page 6. Look for the deleted note title in the list | Deleted note title is NOT present in the UI notes list No ghost entries are visible | High | Not Started
TC-011 | SC-008 | Negative UI - Wrong Credentials | Login page is open | 1. Enter wrong@email.com in the email field 2. Enter wrongpass in the password field 3. Click the Login button | Error message is shown on screen User is NOT redirected to the notes page | High | Not Started
TC-012 | SC-009 | Negative API - GET /notes Without Token | No auth token is being used | 1. Send GET /notes request with no x-auth-token header | API returns status 401 Unauthorized | High | Not Started
TC-013 | SC-009 | Negative API - DELETE Non-Existent Note | Valid auth token is available | 1. Send DELETE /notes/nonexistent-id-999 with valid token | API returns status 404 Not Found | Medium | Not Started
TC-014 | SC-009 | Negative API - Create Note With Missing Fields | Valid auth token is available | 1. Send POST /notes with an empty JSON body {} | API returns status 400 Bad Request Response contains a validation error message | Medium | Not Started

## 4. Test Data
Data ID | Data Type | Test Data | Usage/Purpose
TD-001 | Valid User Credentials | Email: thabassum641@gmail.com Password: abcDEF123$%^ | Used for valid login TC-001, TC-004, TC-005, TC-008, TC-010
TD-002 | Invalid User Credentials | Email: hello123@gmail.com Password: wrongpass123 | Used for negative login scenarios TC-002, TC-011
TD-003 | Empty Credentials | Email: Password: | Used for empty field validation TC-003
TD-004 | Valid Note - UI Creation | Title: My Test Note Description: Created from UI test Category: Home | Used for UI note creation TC-004, TC-005
TD-005 | Valid Note - E2E Sync Test | Title: E2E Note Description: Sync check Category: Work | Used for E2E UI to API sync check TC-008
TD-006 | Valid Note - Delete Test | Title: UI Delete Test Description: Check UI after delete Category: Personal | Used for API delete and UI verify TC-009, TC-010
TD-007 | API Auth Token | Obtained dynamically via POST /users/login Stored in request header as x-auth-token | Used for all API test cases
TD-008 | Non-Existent Note ID | ID: nonexistent-id-999 | Used for negative API test TC-013
TD-009 | Empty API Request Body | JSON body: {} | Used for missing fields validation TC-014
TD-010 | Performance Threshold | Maximum allowed response time: 2.0 seconds | Used for API performance check TC-007

## 5. Test Execution
Test Case ID | Cycle | Test Case Title | Executed By | Exec Date | Pass/Fail | Defect ID | Remarks
TC-001 | Cycle-1 | Valid UI Login | QA User 1 | 06-05-2026 | Pass |  | Login redirects correctly
TC-002 | Cycle-1 | Invalid UI Login - Wrong Password | QA User 1 | 06-05-2026 | Pass |  | Error message displayed as expected
TC-003 | Cycle-1 | Invalid UI Login - Empty Fields | QA User 1 | 06-05-2026 | Pass |  | Validation error shown correctly
TC-004 | Cycle-1 | Create Note via UI - All Fields | QA User 1 | 06-05-2026 | Pass |  | Note created successfully
TC-005 | Cycle-1 | Note Visible Immediately After Creation | QA User 1 | 06-05-2026 | Pass |  | Note appeared without page refresh
TC-006 | Cycle-1 | API GET /notes - Status and Schema | QA User 1 | 06-05-2026 | Pass |  | Status 200 returned with correct list
TC-007 | Cycle-1 | API GET /notes - Response Time < 2s | QA User 1 | 06-05-2026 | Pass |  | Response received in 0.4 seconds
TC-008 | Cycle-1 | UI-Created Note Matches API | QA User 1 | 06-05-2026 | Pass |  | Title and description matched exactly
TC-009 | Cycle-1 | Delete Note via API | QA User 1 | 06-05-2026 | Pass |  | Note removed from API list successfully
TC-010 | Cycle-1 | API-Deleted Note Gone from UI | QA User 1 | 06-05-2026 | Pass |  | Note absent from UI after refresh
TC-011 | Cycle-1 | Negative UI - Wrong Credentials | QA User 1 | 06-05-2026 | Pass |  | Error message shown correctly
TC-012 | Cycle-1 | Negative API - GET Without Token | QA User 1 | 06-05-2026 | Pass |  | Status 401 returned as expected
TC-013 | Cycle-1 | Negative API - DELETE Non-Existent | QA User 1 | 06-05-2026 | Pass |  | Status 404 returned as expected
TC-014 | Cycle-1 | Negative API - Missing Fields | QA User 1 | 06-05-2026 | Pass |  | Status 400 returned as expected

## 6. Traceability Matrix
Requirement ID | Test Case ID | Requirement Description | Test Coverage | Status
FR-01 | TC-001 TC-002 TC-003 | UI Login should work | Covered | Completed
FR-02 | TC-004 | Create note via UI | Covered | Completed
FR-03 | TC-005 | Note should appear instantly in UI list | Covered | Completed
FR-04 | TC-006 TC-007 | API GET /notes returns list | Covered | Completed
FR-05 | TC-008 | UI-created note must appear in API | Covered | Completed
FR-06 | TC-009 | Delete note via API | Covered | Completed
FR-07 | TC-010 | Deleted note must disappear from UI | Covered | Completed
FR-08 | TC-007 | API response must be less than 2 seconds | Covered | Completed
FR-09 | TC-011 TC-012 TC-013 TC-014 | Negative scenarios for UI and API | Covered | Completed

## 7. Defect Report
Defect ID | Test Case ID | Defect Title | Defect Description | Severity | Priority | Status | Assigned To | Found Date | Remarks
DEF-001 | TC-004 | Application does not handle note titles above 100 characters | After entering a note title with more than 100 characters, the note is not created successfully and no proper validation message is displayed. | medium | medium | Open | Dev Team | 2026-05-09 | Boundary value validation issue observed
DEF-002 | TC-007 | UI response time exceeds 2 second threshold | UI page taking more time to load.ie 5-10 seconds . going to exceed 10 only if network is slow | Low | Low | Open | Backend Team | 06-05-2026 | Intermittent issue - needs performance profiling

## 8. Test Summary Report
TEST SUMMARY REPORT
PROJECT INFORMATION
Project Name: | Notes App — UI + API Hybrid Automation (ExpandTesting)
Test Cycle: | Cycle-1
Report Date: | 06-05-2026
Prepared By: | Saniya Thabassum
EXECUTION SUMMARY
Total Test Cases: | 16
Test Cases Executed: | 16
Test Cases Passed: | 16
Test Cases Failed: | 0
Pass Percentage: | 100
DEFECT SUMMARY
Total Defects: | 2
Critical Defects: | 0
High Defects: | 0
Medium Defects: | 1
Low Defects: | 1
Open Defects: | 2
Closed Defects:
CONCLUSION
Testing Status: | In Progress
Release Readiness: | Pending Defect Resolution
Overall Recommendation: | Application is functionally stable for core flows such as login, note creation, and E2E sync. DEF-001 (note not visible without refresh) must be fixed before release. DEF-003 (API returns 200 without auth token) is a security issue and must be fixed before release. DEF-002 (slow UI response) to be monitored in staging environment.
REMARKS