## 0. Guidance & Instructions
MANUAL TESTING DOCUMENTATION GUIDE
1. TEST PLAN
Purpose: Defines overall testing approach, scope, timeline, and resources.
Key Components: Project info, scope, testing types, environment, timeline, resources, risks, assumptions.
Who fills it: QA Lead/Test Manager
When: Before testing begins
2. TEST SCENARIOS
Purpose: Describes high-level business situations/workflows to be tested.
Key Components: Scenario ID, name, description, pre-conditions.
Who fills it: QA Lead/Business Analyst
When: During test planning phase
Example: "User Login Scenario" - User provides credentials and system validates them
3. TEST CASES
Purpose: Detailed step-by-step instructions for testing specific functionality.
Key Components: Test case ID, scenario ID, title, pre-conditions, steps, expected result, priority.
Who fills it: QA Engineer/SDET
When: During test design phase
Best Practice: Each test case should be independent and reusable
4. TEST DATA
Purpose: Documents all test data needed for test execution.
Key Components: Data ID, type, test data values, purpose/usage.
Who fills it: QA Engineer/Test Data Manager
When: Before test execution
Important: Use realistic but safe data; never use real production data
5. TEST EXECUTION DOCUMENT
Purpose: Records actual execution results of test cases.
Key Components: Test case ID, cycle, title, executed by, execution date, pass/fail status, defect ID.
Who fills it: QA Engineer
When: During test execution
Status Options: Pass (expected behavior matches actual), Fail (discrepancy found), Not Executed (skipped)
6. TRACEABILITY MATRIX
Purpose: Maps requirements to test cases to ensure complete coverage.
Key Components: Requirement ID, test case ID, requirement description, coverage status.
Who fills it: QA Lead
When: Throughout testing lifecycle
Benefit: Identifies gaps; ensures all requirements are tested
7. DEFECT REPORT
Purpose: Documents all defects/bugs found during testing.
Key Components: Defect ID, test case ID, title, description, severity, priority, status, assigned to.
Who fills it: QA Engineer
When: When defect is discovered
Severity: Critical (blocks functionality), High (major issue), Medium (moderate impact), Low (minor issue)
Priority: Should be set based on business impact
8. TEST SUMMARY REPORT
Purpose: High-level overview of testing results and recommendations.
Key Components: Execution summary, defect summary, metrics, conclusion, recommendation.
Who fills it: QA Lead/Test Manager
When: At end of test cycle
Audience: Stakeholders, Project Manager, Development Lead
KEY METRICS
Pass Rate = (Test Cases Passed / Test Cases Executed) × 100%
Requirement Coverage = (Requirements Tested / Total Requirements) × 100%
Defect Density = Total Defects / Total Test Cases
Escape Rate = Defects found in production / Total defects found (in testing + production)

## 1. Test Plan
TEST PLAN
Project Name: | Notes App — UI + API Automation
Test Plan ID: | TP-001
Version: | 1.0
Date: | 06-05-2026
Prepared By: | Saniya Thabassum
Approved By: | QA Lead
SCOPE
Features to be Tested: | 1. UI Login (valid and invalid)
2. Create Note via UI
3. Note visible in UI instantly after creation
4. API GET /notes - list and response time
5. UI-created note matches API response
6. Delete note via API
7. API-deleted note disappears from UI
8. Negative UI and API scenarios
Out of Scope | 1. Performance load testing
2. Mobile browser testing
3. Third-party integrations
TESTING TYPE
Functional Testing | ☐
Regression Testing | ☐
Integration Testing | ☐
UAT | ☐
TEST ENVIRONMENT | Dev / QA / Staging / Production
Application URL(UI) | https://practice.expandtesting.com/notes/app
Application URL(API) | https://practice.expandtesting.com/notes/api
Browser | Chrome (latest version)
Operating System | Windows 11
Test Framework | Selenium + Python + Pytest + Requests
TIMELINE | 2026-05-06
Start Date: | 2026-05-08
End Date:
RESOURCES
QA Lead: | Static credentials in config.yaml + dynamic API data
QA Resources:
Test Data Provider:
RISKS & ASSUMPTIONS
Risks
Risk 1: | Locators may change with application updates
Risk 2: | API token may expire during long test runs
Risk 3: | Network latency may affect response time assertions
Assumptions:
Assumption 1 | Test account is pre-created on ExpandTesting
Assumption 2 | Application is accessible during test execution
Assumption 3 | Python 3.10+ and Chrome browser are installed

## 2. Test Scenarios
Scenario ID | Scenario Name | Description | Pre-conditions
SC-001 | UI Login - Valid Credentials | Validate that a registered user can log in successfully using valid email and password via the Notes App UI. | User account exists on ExpandTesting App is accessible
SC-002 | Create Note via UI | Validate that a logged-in user can create a new note by entering Category, Title and Description and clicking Save. | User is logged in Notes list page is open
SC-003 | Note Appears Instantly in UI Without Refresh | Validate that after saving a note, it appears in the notes list immediately without requiring a page reload. | User is logged in Note creation form is submitted
SC-004 | API GET /notes Returns List | Validate that the GET /notes endpoint returns status 200, a list of notes, and responds within 2 seconds. | Valid API auth token obtained via POST /users/login
SC-005 | UI-Created Note Matches API Response | Validate end-to-end consistency: a note created in the UI must appear in the API GET /notes response with matching title and description. | User logged in on UI API client authenticated
SC-006 | Delete Note via API | Validate that sending DELETE /notes/{id} removes the note and subsequent GET /notes no longer returns it. | Note exists in system API client authenticated with valid token
SC-007 | API-Deleted Note Disappears from UI | Validate that after deleting a note via API, refreshing the UI notes list shows the note is gone with no ghost entries. | Note exists in both UI and API API client authenticated
SC-008 | Negative UI Scenarios | Validate that the UI correctly handles invalid inputs: wrong credentials show an error message and empty fields are rejected. | Notes App login page is accessible
SC-009 | Negative API Scenarios | Validate that the API returns correct HTTP error codes: 401 for missing token, 404 for non-existent note, 400 for missing fields. | API endpoint is accessible

## 3. Test Cases
Test Case ID | Scenario ID | Test Case Title | Pre-conditions | Steps | Expected Result | Priority | Status
TC-001 | SC-001 | Valid UI Login | Login page is open Valid account exists on ExpandTesting | 1. Open the login page 2. Enter valid email address 3. Enter valid password 4. Click the Login button | User is redirected to the Notes list page URL contains /app | High | Not Started
TC-002 | SC-001 | Invalid UI Login - Wrong Password | Login page is open | 1. Open the login page 2. Enter valid email address 3. Enter wrong password 4. Click the Login button | Error message is displayed on screen User remains on the login page | High | Not Started
TC-003 | SC-001 | Invalid UI Login - Empty Fields | Login page is open | 1. Open the login page 2. Leave email field blank 3. Leave password field blank 4. Click the Login button | Validation error is shown Form is not submitted | Medium | Not Started
TC-004 | SC-002 | Create Note via UI - All Fields | User is logged in Add Note button is visible | 1. Click the Add Note button 2. Select Category as Home 3. Enter Title: My Test Note 4. Enter Description: Test description text 5. Click the Save button | Success message is displayed Note appears in the notes list | High | Not Started
TC-005 | SC-003 | Note Visible Immediately After Creation | User is logged in Note has just been created via TC-004 | 1. Complete note creation steps from TC-004 2. Do NOT refresh the page 3. Observe the notes list on screen | Newly created note title is visible in the list No page reload was needed | High | Not Started
TC-006 | SC-004 | API GET /notes - Status and Schema | Valid auth token has been obtained | 1. Send POST /users/login with valid credentials to get token 2. Send GET /notes with header x-auth-token set to the token | Status code is 200 Response body contains key called data data is a list Each item has id, title, description and category | High | Not Started
TC-007 | SC-004 | API GET /notes - Response Time Less Than 2 Seconds | Valid auth token has been obtained | 1. Send POST /users/login 2. Send GET /notes 3. Record the elapsed response time | Response time is less than 2.0 seconds | High | Not Started
TC-008 | SC-005 | UI-Created Note Matches API - Title and Description | User is logged in on UI API client is authenticated | 1. Create note via UI with Title: E2E Note and Description: Sync check 2. Send GET /notes via API 3. Find the note in API response where title equals E2E Note 4. Compare the description field | API response contains the note Title matches exactly Description matches exactly | High | Not Started
TC-009 | SC-006 | Delete Note via API - Confirmed Removal | Note exists in the system API client is authenticated | 1. Send POST /notes via API to create a note and capture the id 2. Send DELETE /notes/{id} via API 3. Send GET /notes via API again | DELETE request returns status 200 Subsequent GET /notes does not contain the deleted note id | High | Not Started
TC-010 | SC-007 | API-Deleted Note Gone from UI | API client is authenticated UI login credentials are available | 1. Create a note via API and capture the id 2. Send DELETE /notes/{id} via API 3. Open browser and login via UI 4. Navigate to notes list page 5. Refresh the page 6. Look for the deleted note title in the list | Deleted note title is NOT present in the UI notes list No ghost entries are visible | High | Not Started
TC-011 | SC-008 | Negative UI - Wrong Credentials | Login page is open | 1. Enter wrong@email.com in the email field 2. Enter wrongpass in the password field 3. Click the Login button | Error message is shown on screen User is NOT redirected to the notes page | High | Not Started
TC-012 | SC-009 | Negative API - GET /notes Without Token | No auth token is being used | 1. Send GET /notes request with no x-auth-token header | API returns status 401 Unauthorized | High | Not Started
TC-013 | SC-009 | Negative API - DELETE Non-Existent Note | Valid auth token is available | 1. Send DELETE /notes/nonexistent-id-999 with valid token | API returns status 404 Not Found | Medium | Not Started
TC-014 | SC-009 | Negative API - Create Note With Missing Fields | Valid auth token is available | 1. Send POST /notes with an empty JSON body {} | API returns status 400 Bad Request Response contains a validation error message | Medium | Not Started

## 4. Test Data
Data ID | Data Type | Test Data | Usage/Purpose
TD-001 | Valid User Credentials | Email: thabassum641@gmail.com Password: abcDEF123$%^ | Used for valid login TC-001, TC-004, TC-005, TC-008, TC-010
TD-002 | Invalid User Credentials | Email: hello123@gmail.com Password: wrongpass123 | Used for negative login scenarios TC-002, TC-011
TD-003 | Empty Credentials | Email: Password: | Used for empty field validation TC-003
TD-004 | Valid Note - UI Creation | Title: My Test Note Description: Created from UI test Category: Home | Used for UI note creation TC-004, TC-005
TD-005 | Valid Note - E2E Sync Test | Title: E2E Note Description: Sync check Category: Work | Used for E2E UI to API sync check TC-008
TD-006 | Valid Note - Delete Test | Title: UI Delete Test Description: Check UI after delete Category: Personal | Used for API delete and UI verify TC-009, TC-010
TD-007 | API Auth Token | Obtained dynamically via POST /users/login Stored in request header as x-auth-token | Used for all API test cases
TD-008 | Non-Existent Note ID | ID: nonexistent-id-999 | Used for negative API test TC-013
TD-009 | Empty API Request Body | JSON body: {} | Used for missing fields validation TC-014
TD-010 | Performance Threshold | Maximum allowed response time: 2.0 seconds | Used for API performance check TC-007

## 5. Test Execution
Test Case ID | Cycle | Test Case Title | Executed By | Exec Date | Pass/Fail | Defect ID | Remarks
TC-001 | Cycle-1 | Valid UI Login | QA User 1 | 06-05-2026 | Pass |  | Login redirects correctly
TC-002 | Cycle-1 | Invalid UI Login - Wrong Password | QA User 1 | 06-05-2026 | Pass |  | Error message displayed as expected
TC-003 | Cycle-1 | Invalid UI Login - Empty Fields | QA User 1 | 06-05-2026 | Pass |  | Validation error shown correctly
TC-004 | Cycle-1 | Create Note via UI - All Fields | QA User 1 | 06-05-2026 | Pass |  | Note created successfully
TC-005 | Cycle-1 | Note Visible Immediately After Creation | QA User 1 | 06-05-2026 | Pass |  | Note appeared without page refresh
TC-006 | Cycle-1 | API GET /notes - Status and Schema | QA User 1 | 06-05-2026 | Pass |  | Status 200 returned with correct list
TC-007 | Cycle-1 | API GET /notes - Response Time < 2s | QA User 1 | 06-05-2026 | Pass |  | Response received in 0.4 seconds
TC-008 | Cycle-1 | UI-Created Note Matches API | QA User 1 | 06-05-2026 | Pass |  | Title and description matched exactly
TC-009 | Cycle-1 | Delete Note via API | QA User 1 | 06-05-2026 | Pass |  | Note removed from API list successfully
TC-010 | Cycle-1 | API-Deleted Note Gone from UI | QA User 1 | 06-05-2026 | Pass |  | Note absent from UI after refresh
TC-011 | Cycle-1 | Negative UI - Wrong Credentials | QA User 1 | 06-05-2026 | Pass |  | Error message shown correctly
TC-012 | Cycle-1 | Negative API - GET Without Token | QA User 1 | 06-05-2026 | Pass |  | Status 401 returned as expected
TC-013 | Cycle-1 | Negative API - DELETE Non-Existent | QA User 1 | 06-05-2026 | Pass |  | Status 404 returned as expected
TC-014 | Cycle-1 | Negative API - Missing Fields | QA User 1 | 06-05-2026 | Pass |  | Status 400 returned as expected

## 6. Traceability Matrix
Requirement ID | Test Case ID | Requirement Description | Test Coverage | Status
FR-01 | TC-001 TC-002 TC-003 | UI Login should work | Covered | Completed
FR-02 | TC-004 | Create note via UI | Covered | Completed
FR-03 | TC-005 | Note should appear instantly in UI list | Covered | Completed
FR-04 | TC-006 TC-007 | API GET /notes returns list | Covered | Completed
FR-05 | TC-008 | UI-created note must appear in API | Covered | Completed
FR-06 | TC-009 | Delete note via API | Covered | Completed
FR-07 | TC-010 | Deleted note must disappear from UI | Covered | Completed
FR-08 | TC-007 | API response must be less than 2 seconds | Covered | Completed
FR-09 | TC-011 TC-012 TC-013 TC-014 | Negative scenarios for UI and API | Covered | Completed

## 7. Defect Report
Defect ID | Test Case ID | Defect Title | Defect Description | Severity | Priority | Status | Assigned To | Found Date | Remarks
DEF-001 | TC-004 | Application does not handle note titles above 100 characters | After entering a note title with more than 100 characters, the note is not created successfully and no proper validation message is displayed. | medium | medium | Open | Dev Team | 2026-05-09 | Boundary value validation issue observed
DEF-002 | TC-007 | UI response time exceeds 2 second threshold | UI page taking more time to load.ie 5-10 seconds . going to exceed 10 only if network is slow | Low | Low | Open | Backend Team | 06-05-2026 | Intermittent issue - needs performance profiling

## 8. Test Summary Report
TEST SUMMARY REPORT
PROJECT INFORMATION
Project Name: | Notes App — UI + API Hybrid Automation (ExpandTesting)
Test Cycle: | Cycle-1
Report Date: | 06-05-2026
Prepared By: | Saniya Thabassum
EXECUTION SUMMARY
Total Test Cases: | 16
Test Cases Executed: | 16
Test Cases Passed: | 16
Test Cases Failed: | 0
Pass Percentage: | 100
DEFECT SUMMARY
Total Defects: | 2
Critical Defects: | 0
High Defects: | 0
Medium Defects: | 1
Low Defects: | 1
Open Defects: | 2
Closed Defects:
CONCLUSION
Testing Status: | In Progress
Release Readiness: | Pending Defect Resolution
Overall Recommendation: | DEF-001 (Application does not handle note titles above 100 characters) DEF-002 (slow UI response) to be monitored in staging environment.
REMARKS | Automation testing completed successfully for UI, API, and E2E scenarios. Most functionalities are working as expected. Two defects were identified during testing: note title boundary handling and slow UI response time. Further optimization and validation improvements are recommended before production release.
in test scenarios given there is no defect but we an imrove it currently written defets which are not actually defect